## 0-3 months
Task | Timeframe | Actions | Success criteria | Status | Remark | Start Date | End Date
Build personal lab | Weeks 1–2 | Create attacker VM + target VMs; snapshot setup | Lab boots and snapshots created | Not started |  | 30/10/2025
Daily practice habit | Ongoing daily | 30–60 min CTF/TH/HTB + 1 tool/command | 21 sessions completed per month | In progress
Notes repo | Week 1 | Initialize GitHub repo "infosec-playbook" | Repo has README and first 10 notes | Completed
Nmap fundamentals | Week 1 | Host discovery and basic scans | Can enumerate hosts and ports reliably | Not started
Web recon basics | Week 2 | Learn Burp Suite proxy and passive recon | Able to find inputs and basic vulns | Not started
SMB/Windows enumeration | Week 3 | Enum shares, users, and services | Extract creds or useful info in lab | Not started
Post‑exploitation basics | Week 4 | Obtain shell, gather creds, basic pivot | Full initial foothold achieved in box | Not started
Weekly public win | Weeks 1–12 | Publish one short LinkedIn post or commit | 12 posts or commits by month 3 | Not started

## 3-9 months
Task | Timeframe | Actions | Success criteria | Status | Remark | Start Date | End Date
Offensive tool mastery | Months 3–5 | Practice Metasploit, Impacket, CrackMapExec | Use tools to compromise lab AD box
Python scripting | Months 3–6 | Write scripts for recon and parsing | One reusable recon script in repo
Windows AD fundamentals | Months 4–7 | Learn Kerberos, LDAP, BloodHound usage | Map domain and identify escalation paths
Web app attacks | Months 4–6 | Practice SQLi, XSS, SSRF labs | Exploit at least 3 web vulns end‑to‑end
Lab hours target | Months 3–9 | Accumulate dedicated lab time | 200+ focused lab hours logged
Practical cert prep | Months 6–9 | PWK/PnPT/eCPPT study and labs | Ready for one practical exam attempt
Publish writeups | Months 3–9 | 3 full exploit/CTF writeups on GitHub | 3 polished writeups with steps
Automate recon workflow | Months 5–8 | Script subdomain, dir, port scan pipeline | Script produces consolidated report

## 9-18 months
Task | Timeframe | Actions | Success criteria | Status | Remark | Start Date | End Date
Choose specialization | Month 9 | Select one path: red team, web, or cloud | One chosen focus documented in repo
Advanced AD emulation | Months 9–12 | Simulate full chain attacks in AD lab | Achieve domain admin in lab exercise
Build a PoC tool | Months 10–14 | Create and publish a small security tool | Tool published with README and tests
Open source contribution | Months 10–15 | Contribute code or docs to a security project | One accepted PR merged upstream
Public technical posts | Months 9–15 | Publish 2 long form posts or detailed writeups | 2 posts with technical depth published
Speak at event | Months 12–18 | Prepare 20 min lightning talk for meetup | Talk delivered or accepted by event
Portfolio readiness | Month 12 | Compile reports, writeups, and repos | Portfolio contains 6+ polished projects
Apply for red team role | Months 12–18 | Target internal/external junior roles | Interviews scheduled and one offer